## Slide 1: LG&E SAP S/4 HANA Project Intro to LG&E Electronics
Linde Confidential

## Slide 2: US External Contractors
Name | SAP Area | Location
Alain Feussi | FICO | NJ
Krithiga Ramu | SD OTC | NJ
Sreenivasrao Amasa | PM | TX
Srinivas Pulkaram | MM | GA

## Slide 3: LG&E Electronics Business
Approximately $0.5B in Sales/Year
    Electronics Specialty Gases Business~ $380M
    Electronics Logistics Business ~ $120M
    Government Lab Business…
Approximately 460 Employees
    370 SAP users
5 Production Plants
1 Lab
15 Warehouses
Chart: 
 | 24 | 18 | 18 | 15 | 13 | 12 | 12 | 12 | 11 | 9 | 9 | 8 | 8 | 7 | 7 | 7 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 44
Bulk He
D2
Halocarbons
He3
HCl
Bulk CO2
NH3
11BF3
HCl3Si
UpTime
Si2H6
HF
N2O
B2H6
NF3
PH3
Equip
WF6
SF6
SiH4
H2SiCl2
Other
Rent
Excimer
C4F8
GeH4
Xe

## Slide 4: Electronics Locations
Office – Headquarters
Hampton, NJ (Jan 2021)
ESG Plant
Medford, OR
ESG Plant
Phoenix, AZ
ESG Plant
Kingman, AZ
ESG Plant
RTP, NC
B11F3 Separation
F2 Synthesis
Si2H6 Purification
CO2 Purification
Corrosives Distillation
Arsine
Phosphine
NH3 Iso’s
N2O Tube Trailers
HCl Transfill
NH3 Distillation
Leadership Team
Customer Service
Logistics
SHEQ
D2 Synthesis
N2O Distillation
Metallic Hydride Mixes
ESG Plant
Alpha, NJ
Ne,Kr,Xe purification
Inert & litho mixes
Halocarbon distillation
He3 purification
Government Lab
New Providence, NJ
USAF Contract Support
(details confidential)
Equipment Ctr
Lopatcong, NJ
New Site Q3 16
Clean rooms 17
Amplify packs
Electronics Logistics
Phoenix, AZ
Warehouse

## Slide 5: SAP Process SMEs
  Finance/Controlling
  David Wright
    Tax/AP/AR/Accounting: Elvir Alicic, Jessica Barloon
    Operations Support: Vivian Ng
  Commercial (OTC/PTP)
  Inventory Management/Warehouse: Angela Radford
      Brad Beesley
      Teresa Follet
      Tina Morse
  Order to Cash: Peggy Lee
  Pricing: Kevin Schmalz
  Export/GTS: Yuliana Kalinova
  Procurement: Derek Holtman
  Operations
  Product to Order: Angela Radford
      Production Planning: Jeff Burnley
      Raw Materials Inventory:
          Mike Unangst
          Gwen Owisney
          Alfredo Meza
      Quality: Courtney Martzen
      Shipping/Receiving
          Alfredo Meza
          Kris Burgess
          Victor Bardales
      Assets: James Liebhart
  Plant Maintenance Lead: Daniel Fiedler
      Process Owner: Rene Garza

## Slide 6: S/4 HANA Technical Transformation Program Roadmap – On Track
Rev Rec
RSE
RUI
RGC
US/Mx
REN
RSP
REW & REE
RAF
S4 projects
Archiving projects
2022
2024
2023
2025
2026
2028
2027
------------ ECC EoL-------------
BOCT EoL
P01
S4 2023
2029
Satellites
SRM / SAPHRON / PI/PO / Solman / GRC-GPU
Satellite Applications
ASEAN & South Asia
P8E SDT
S4
2021
S4
2021
S4 2023
S4 2023
S4 2023
S4 2025
S4 DEV box; access to regions for verifications
Mobilization
Mobilization
Mobilization
Mobilization
Mobilization
Mobilization
Mobilization
IC1
S4
2021
S4
2021
22.01.24
8.09.24
Greater China (RGC)
P6E SDT
16.02.25
11.08.25
19.02.24
01.09.23
US & Mexico
P2E SDT
RAF
P9E SDT
09.03.26
LT (RSP)
PEA SDT
21.02.27
01.02.26
Impress (REN)
P01 SDT
19.09.27
01.09.26
01.01.23
InTouch (REW/REE)
GPA SDT
14.05.28
01.04.27
01.07.22
01.03.23
01.08.23
01.05.24
01.10.25
01.02.26
01.03.25
P9E
P2E
PRD
PEA
Technical Clean-Up
REW/REE GPA
P8E
RUI
PRD SDT
Mobilization
Mobilization
01.04.23
01.06.24
05.11.24
01.06.23
01.04.23
BOCT
P6E
01.08.24
IC5
IC4
IC2
Pre-projects
eWM, FI CoA etc.
Readsoft, SAP FSM, TeleQuery etc.
GTS
Rev Rec
IC3
APO Replacement
PI/PO 2025
Today
01.03.25
Program includes S/4HANA Projects and Satellites
Technical Transformation
Learnings from former projects
Balance Corp resources between different projects
BOCT End of Life timeline
CAPEX approval in IC3
Planning of 2025 activities

## Slide 7: Project S/4 HANA US & Mexico Project Plan
2024
Dec
Jan
Feb
Mar
April
May
xyz
June
Regional
Corporate
Test Automation Build
Aug
Sep
July
Analyze &
Design
Mobilization
Create Test Strategy & Plan
System
build
Development
&
Functional
xyz
(Add-On)
Reporting
Onboarding & Plan
SDT
Develop
Archiving execution
Archiving completed
Archiving
SDT MBP
Approach
Build Training Material
Functional Unit Testing
Build & Config & Unit Testing
Development
Oct
Nov
Dec
Jan
Project Start
Change Mgt.
TM1 (T8A), SRC2
Single Role Build
Job/Composite Role Design
Job/Comp. Role Build
SAP
Authorization
TM0, SRC1
BW Queries & S4 HANA Gap analysis & build
Local extractor analysis & build
Dashboard analysis & configure
SIT
Go Live
TM2
GL Sim
TM2, SRC1
GLS (T8A)
Productive P2A
Hypercare
Functional Data Val.
2 weeks
6 weeks
6 weeks
15 weeks
Hypercare
Go Live
Dual Maintenance
Prep
Train-the-Trainer
Related Projects
5 weeks
Project
Soft Freeze
DR
1 week
8 weeks
12 weeks
8 weeks (18.8. -10.10.)
5 weeks (3.3. – 04.04.)
14 weeks
Project Management (Financial, Gov)
Interface Planning
Add-Ons
6 weeks
Dev BW to GDR
Analysis
Kick Off
TM0
11 weeks (07.04. – 20.06.)
TM1
8 weeks (23.06. – 15.08.)
EU Training
Vacation period
Feb
March
April
Cut Over
6 weeks
6 weeks (13.10. – 21.11.)
2025
Single Role Design
2026
Testing
27 weeks
6 weeks
Change Freeze
TM0 Unit Test
Dress Reh
3 weeks (2. – 20.02.)
09.03.26
Cut Over Prep
UAT
Functional Data Validation
9 weeks (24.11. – 23.1.)
Single Role Test
Comp. Role Test
Mapping EU
EU Simulation

## Slide 8
SRC2
SRC1
ECC 6
D2A
S/4
System Landscape
Project Approach
Q2A
P2A
DGE
S2E
P2E
Source
Target
Control Sys
PMG
Current Operational Landscape
Project
Landscape
Box 1
System Copy post Go Live
Full Prod System Copy prior to Migration
Go Live
Transport Catch Up
Retrofit
Data Migration
Data Migration
TM1 S4A
(SIT)
TM2 Q2A
(UAT)
Box 2
Box 1
Box 2
TM0 S3A
(Unit Tests)
Go Live Simulation S4A
Future Operational Landscape

## Slide 9: Appendix

## Slide 10: Key SAP Integrated Applications
Application | Description | Business Contacts | Technical Contacts
TLIMS | Metrology data from analyzers | Patricia Clarke, Lisa Moralez | Mark Douglass (Trinity Data Solutions)
Vertex | Tax | Mark Mezera, Tina Sylvester | Johannes Schneider Lazar
Prometheus | Plant Maintenance | Daniel Fiedler | Stuart Boyd
Exstream (Streamserve) | Billing | Kevin Schmalz | Stuart Boyd, Nathusingh Rathod
Evolve (Winshuttle) | Forms/workflow processes | Kevin Schmalz | Stuart Boyd
GTS | Export & trade compliance | Yuliana Kalinova | Martin Gall, Uwe Jung
EPP | Handheld cylinder scanning | Angela Radford | Stuart Boyd, Brendan Farthing
SRM | Procurement | Oscar Ramos | Stuart Boyd
MES (In development) | Production automation | Neil Cope, Won Bernhardt | Stuart Boyd