## Slide 1: SAP S4 HANA Technical Transformation Project, US/MX Satellites Overview
March 10-14, 2025

## Slide 2: US-MX HANA Satellites Overview Introduction
Purpose/questions that will be answered:
What are Satellite systems
Why are we testing
Identify the test phases and the corresponding preparation phases
What is the purpose/reasoning for the various phases
The timing and duration of the phases
What do we need from you

## Slide 3: US-MX HANA Satellites Overview Satellite Lead Introduction
Responsibilities
Key activities (high level)
Identify the connected systems/services (aka satellites).
Identify owners, key technical/functional resources and vendors.
Align on priority, criticality, and timing.
Understand the requirements for connectivity such as effort, business data, technical configuration etc.
Test preparation
Ensure services are available for testing as per the agreed schedule.
Ensure services are available for go live as per the agreed schedule.
Provide support during test phases and go live.
Manage assigned defects, ensuring timely resolution and escalate as required.
Minimize impact to business operations.

## Slide 4: US-MX HANA Satellites Overview Satellite Overview
What are satellites
Satellite systems are separate, specialized applications that are not part of the core SAP ECC (ERP Central Component) or S/4 HANA system but are integrated with it to handle specific business functions.
Types of satellites
  Technical - focuses on the underlying system infrastructure and technical aspects like data management, system administration, and integration
  Functional - business-focused components designed to deal with user interaction and address specific business needs like sales, finance, or HR.
What are the different ways satellites interface with SAP
  PI/PO (Process Integration/Process Orchestration)
  RFC (Remote Function Call)
  FTP (File Transfer Protocol)
  Flat Files
  File Shares
  Database access

## Slide 5: Project S/4 HANA US & Mexico – Scoping Satellites in scope
Country | US/Mex | US | MX | US | US | US | MX | US | US | US | US | US | US | US/Mex | MX | US | US/Mex | US | US/Mex | US
Satellite Owner(s) | Alastair Kerswell Mritunjay Kumar Saw | Stuart Boyd | Stuart Boyd | Jürgen Mohr Mala Mani Catherine Alberni | Stuart Boyd | SRM Team | SRM Team | Sunil N Subeydhi | Kevin Schmalz | Nathusingh Rathod Vendor support | Brendan Farthing | Armin Pfeiffer Martin Gall | Jim Hardenbrook | Anders N Eriksson Stuart Boyd | Juan Romero | Nathusingh Rathod | Shweta Chaudhary Balaji Soundarrajan | Peter Casazza Patricia Clarke Lisa Moralez | Peter Kerschl Tomas Boldizar | Mark Mezera
Satellite applications | Archive: IXOS/Opentext | Banking: BOA Banking: JPM | Banking: CITI | BW | Data Warehouse Extracts (FTP from SAP) | EDI | EDI: Grainer MX Orders | EDI: LGE Electronics Delivery Advice | Evolve | Extreme | Fiori BTP (Custom) | Global Trade System (GTS) | Perceptive Content | Promethus | RPA | Spectra | SRM | TLIMS | UC4 | Vertex
Interface | SAP PI/PO, RFC, FTP, Flat file, DB Access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Core systems | SAP S/4 HANA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: US-MX HANA Satellites Overview Master List
Refer to the RNA_interface list.xlsx for satellite information
Sample only shown here,
exhaustive list stored in link referenced

## Slide 7: US-MX HANA Satellites Overview Considerations
  Information needed for the satellites
    Identify the satellites that are in use
    Identify the type, technical or functional
    Identify the satellites that are in scope with each phase of testing
    Identify key individuals
      Functional Expert(s)/Technical Expert(s)/Business owner/Expert User(s)
    Resources required to connect
      Technical Accounts
      End User Accounts
      File Shares
      Software Packages
    Platform capability:
      Compatibility - does it support S/4? Will it support S/4? Do we need to upgrade or install a package to make it compatible?
      Licensing - can it connect to additional systems?
      Support – Do we have a support agreement with the vendor
      Capability – Can it connect to multiple systems at once or will we need to switch during testing
    Documented processes to connect, configure and test

## Slide 8: US-MX HANA Satellites Overview Environments/Test Phases
Shell Testing on Development S/4 environment
    Subset of satellites connected to the permanent development S/4 client.
    Very limited data, short test period.
    This is to confirm the system is setup correctly, that the core business processes are working and that the satellite applications are connected and able to interface with S/4 HANA.
    Testing owned by Corp IT, supported by regions
FUT – Functional Unit Testing on Development S/4 environment
    Satellites connected to the permanent development S/4 client. Limited data, longer test period.
    Unit test the subset of satellites connected. Test the individual system components. Identify and fix fundamental issues.
    Testing by Regional IT - Functional, supported by Regional Technical and Corp IT - Functional/Technical teams
TM0 Unit Testing – Functional Unit Testing on migrated TM0 environment
    First migration, data possibly not fully suitable for integration, with no satellites connected to temporary test S/4 client
    FUT testing with the first migrated data
    Testing by Regional IT - Functional, supported by Regional Technical and Corp IT- Functional/ Technical teams

## Slide 9: US-MX HANA Satellites Overview Environments/Test Phases
SIT - Systems Integration Testing on migrated TM1 environment
    Satellites connected to a temporary quality S/4 client, copy of production data.
    Confirm all satellites, functional and end to end business process are working.
    Testing by Regional IT - Functional, supported by Regional Technical and Corp IT - Functional/ Technical teams
UAT – User Acceptance Testing on migrated TM2 environment
    Satellites connected to the permanent quality S/4 client , copy of production data.
    Verify all the end to end business processes are functioning according to specifications.
    Testing by Regional Business, supported by Regional and Corp IT - Functional / Technical teams
GLS – Go Live Simulation on migrated GLS environment
    Some satellites connected to a temporary quality S/4 client , copy of production data. Health checks (only)
    Checks by Regional IT - Functional, supported by Regional Technical and Corp IT - Functional/ Technical teams
Cutover – Go Live on S/4 Production environment
    All satellites connected to the permanent production S/4 client , full production data
    Health checks (with selective tests) by Regional IT - Functional and possibly key business users
    Supported by Regional Technical and Corp IT - Functional/ Technical teams

## Slide 10: US-MX HANA Satellites Overview Timeline
2024
Dec
Jan
Feb
Mar
April
May
xyz
June
Regional
Corporate
Aug
Sep
July
Analyze &
Design
Mobilization
System
build
Development
&
Functional
Reporting
SDT
Develop
Archiving execution
Archiving
Approach
Build Training Material
Development
Oct
Nov
Dec
Jan
Project Start
Change Mgt.
Single Role Build
Job/Composite Role Design
Job/Comp. Role Build
SAP
Authorization
BW Queries & S4 HANA Gap analysis & build
Local extractor analysis & build
Hypercare
Go Live
Dual Maintenance
Prep
Train-the-Trainer
Related Projects
Project
Soft Freeze
Project Management (Financial, Gov)
Analysis
EU Training
Vacation period
Feb
March
April
Cut Over
2025
2026
Testing
Change Freeze
Mapping EU
EU Simulation
Single Role Design
Test Phases – Red Boxes
Data Migration – Yellow Boxes
System Preparation – Green
Test Automation Build
Create Test Strategy & Plan
Onboarding & Plan
Archiving completed
SDT MBP
Build & Config & Unit Testing
TM0, SRC1
Dashboard analysis & configure
DR
Interface Planning
Kick Off
Hypercare
Cut Over Prep
Functional Unit Testing
TM2
TM1
GL Sim
SIT
Functional Data Val.
Dress Reh
UAT
Functional Data Validation
GLS (T8A)
TM2, SRC1
TM1 (T8A), SRC2
production P2A
TM0 Unit Test
TM0
# Refer to the SAP S4 US & Mexico Project Governance.pptx for the Project plan.
8 Weeks
8 Weeks
11 Weeks
6 Weeks
9 Weeks
6 Weeks
3 Weeks
15 Weeks
6 Weeks
2 Weeks
12 weeks

## Slide 11: US-MX HANA Satellites Overview Possible Limitations
Satellite Test systems not always available, especially when dealing with third parties such as banks, customers or suppliers .
Some tests may have to be simulated and/or involve comparisons of results with ECC.
Where satellite owners reside outside regional/corporate IT, early alignment and commitment of support needs to be ensured
Some satellites can only support one test environment and must be switched between systems.
There may be some different setups or the way some satellites are used between regions.
Connected systems may be required for production support or business critical enhancements. Testing needs to be planned accordingly.
Prioritize satellites applications relating to cutover.
All involved must have a clear understanding of configuration/setup. Ensure documentation, functional/technical resources and, if required, suppliers are available.

## Slide 12: Thank you for your attention.