## Slide 1: S/4 HANA Migration SAP ECC - Mexico
March 2025
Leticia Mellado

## Slide 2
Approximately $0.5B in Sales/Year
    Electronics Specialty Gases Business~ $380M
    Electronics Logistics Business ~ $120M
    Government Lab Business…
Approximately 460 Employees
    370 SAP users
5 Production Plants
1 Lab
15 Warehouses
Chart: 
 | 24 | 18 | 18 | 15 | 13 | 12 | 12 | 12 | 11 | 9 | 9 | 8 | 8 | 7 | 7 | 7 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 44
Bulk He
D2
Halocarbons
He3
HCl
Bulk CO2
NH3
11BF3
HCl3Si
UpTime
Si2H6
HF
N2O
B2H6
NF3
PH3
Equip
WF6
SF6
SiH4
H2SiCl2
Other
Rent
Excimer
C4F8
GeH4
Xe
S/4 HANA Migration SAP ECC - Mexico

## Slide 3
ECC
SAP Business Suite for SAP HANA (SAP S4HANA or short S4) architecture shift to ‘in-memory’ HANA database, User Interface mobile centric (FIORI)
SAP ERP Central Component (SAP ECC) runs on ‘classic’ SQL (ORACLE) database –
end-of-life 2025/ 27
SAP technology transformation required as opposed to JDE upgrade from 9.0 to 9.2 being ‘just’ a technology migration / upgrade
established
2004
retires
2025 - 2027
established
2015
retires earliest
2040
Impact
Technology change requires landscape Transformation as opposed to Upgrade
In-Memory Database
Much higher application and integrated systems performance (in-build Analytics, e.g. eChannel benefits)
Significant Data Model changes, code and data conversion projects
In-memory TB cost factors more expensive, need to reduce data volumes (Archiving: 2y data retention)
SAP Application Suite
SAP is renovating most of the peripheral suite applications in parallel
Linde must address ~40 systems as part of the landscape transformation
Some system migrations, some replacements
Business
Albeit multiple workshops with SAP and Linde experts, insignificant benefits for gases business identified
Hence technical transformation program required (a.k.a. Brownfield)
S/4 HANA Migration SAP ECC - Mexico
Notes: S/4 HANA is considered a different product to ECC, it is not an upgrade release to ECC​!
HANA = Hasso’s New Architecture or High-Performance Analytic Appliance

## Slide 4: S/4 HANA Technical Transformation Program Selective Data Transition (SDT)
ECC System is converted “in place”: the former ECC system becomes an S4 system at cutover
Code AND Data is converted using the SAP standard Software update manager (SUM) at cutover
Two major disadvantages
  Required preparation projects driven by S4 changes (“simplification”) with significant overhead
  BOCT EHP0 End of Live is 2025 – with SUM, we could not make that date for BOCT systems
SDT separates code conversion from data migration
  Minimizing pre-project overhead e.g. New Ledger, CVI, etc. data issues handled as mappings
  Allows Linde to transform BOCT with EoL 2025
  Enables regions for staggered go-lives (RSE, potentially InTouch regions later)
Standard ECC-S4 Conversion Approach: “In Place Conversion”
Data Migration Approach: “Selective Data Transition”
“In place”
Code/Customization conversion decoupled from data migration
“Shell” System Conversion, fixing only what is necessary
SDT tool supported Data Migration
Existing
New
Existing
Existing Converted

## Slide 5: S/4 HANA Technical Transformation Program Program Organization
Project Level
RSE
Deployment Manager
Sujoy Sen
Regional IT
Corporate Function
Global
Program Manager
Stephan Domes
RSP
Deployment Manager
Damian Noll
APAC
Program Manager
Leon Xu
RUI
Deployment Manager
Neil Kitchen
EMEA
Program Manager
Husein Hassen
REW/REE
Deployment Manager
tbd
APAC IT Jour Fix
Jason O’Brien,
Michael Kurtz*,
Goran Cederwall
Americas IT Jour Fix
Dulce Borjas, Adrian Espinosa, P. Casazza, Michael Kurtz*, Goran Cederwall, Nat T., K. Conrad
RGC
Deployment Manager
Dewey Chen
US & Mex
Deployment Manager
Derek Punaro,
Leticia Mellado
Delivery Integration
Nat Thiyagarajan
Platform Solution
Design
Tobias Hust
Program Controlling
Katharina Conrad
RAF
Deployment Manager
Husein Hassen
REN
Deployment Manager
tbd
*Invited on request
SDT
Tobias Hust
Infrastructure
Thomas Gerulat
PMO
Sneha Dutta
Jana Leibiger
Simona Roth
Americas
Program Manager
n/a
S/4 HANA Program SteerCo
Denny Brown
Leon Xu, Danny Perri, Dulce Borjas*
Adrian Espinosa, P. Casazza, Michael Kurtz,
Goran Cederwall, Nat T., K. Conrad etc.
EMEA IT Jour Fix
Danny Perri,
Michael Kurtz*,
Goran Cederwall

## Slide 6: Project S/4 HANA US & Mexico – Scoping Overview
Overall approach is to keep the functionality as is, i.e., all functionality which is currently in operations as on Dec 2024 will be delivered in S/4HANA, unless it is mandated by SAP as change in the Simplification or Compatibility list.
Only active legal entities (company codes) will be migrated to S/4HANA
User roles will be reorganized to factor S/4HANA role concepts and new transactions.
All existing Satellites (including SRM and GTS) and interfaces will continue.
In FICO, following are the mandatory changes –
  New GL, new Asset Accounting, Material Ledger
  Customer/Vendor Integration (CVI)
Only mandatory Fiori apps will be included (replacement of an existing transaction code, optional ones will be enabled but not promoted).
Data Archiving is a pre-requisites (2 years plus current year data will reside in SAP & 10 years retained in IXOS Archive)
Regional BW will be replaced by Global SAP BW (GPR)
All Data extractors (e.g. Informatica) and impacted reports will be adjusted to new S/4HANA structures.
Own separate US & Mexico Development environment(s) decision taken
Hosting landscape location is T-Systems (Frankfurt, Germany)

## Slide 7: Project S/4 HANA US & Mexico – Scoping Functional decisions signed off by US and MX
Functionality | Comments | Country in scope
1. Universal Journal (new GL) (integrated FI & CO) | Consolidated single table across FI & CO with real-time reconciliation of Financial Accounting with Controlling & Fixed Assets | US/MX
2. Business Partner | Integrated Business Partner master data as parental node for customer, vendor, and other partners (only technical activation, no streamlining of customers and vendors as part of project) | US/MX
3. Material Ledger | Technical activation with S/4HANA go live, for potential future use delivering more detailed material costing | US/MX
4. Financial Supply Chain Management | Mandatory migration from ECC Credit Management | US/MX
5. Parallel Ledgers | Leverage Universal Journal (new GL) and activate parallel ledgers for group/local tax / local reporting | US/MX
6. Document Split | Splitting Balance Sheet accounts by lines of business (not seen as relevant for both US and MX given the singular business model) | Not required for both
7. Account Based Customer Profitability (COPA) | Technical activation to allow real-time reconciled Customer Profitability with General Ledger. Existing costing based COPA will continue in parallel, to allow business multiple months before switching to account based COPA | US only

## Slide 8: S/4 HANA Technical Transformation Program Project Work Packages
Project Work Packages to be adjusted to local project:
Mobilization
  Archiving
  Financial and contractual activities
  Project Preparation (team onboarding, KT-sessions, planning, Project Governance)
  S/4 HANA Activities (Simplification & Compatibility, Interfaces, Reporting, Testing & Auto, Roles, Add-Ons)
  Shell Conversion
Roles
  Single Role Design & Build
  Composite Role Design & Build
  End User Simulation
SDT Migration
  Migration Blueprint
  Technical Migration 0, 1 and 2
  Go Live Simulation
Testing
  Functional Unit Test
  TM0 Unit Testing
  System Integration Test
  User Acceptance Test
  Automation Test

## Slide 9: Project S/4 HANA US & Mexico Project Plan
2024
Dec
Jan
Feb
Mar
April
May
xyz
June
Regional
Corporate
Test Automation Build
Aug
Sep
July
Analyze &
Design
Mobilization
Create Test Strategy & Plan
System
build
Development
&
Functional
xyz
(Add-On)
Reporting
Onboarding & Plan
SDT
Develop
Archiving execution
Archiving completed
Archiving
SDT MBP
Approach
Build Training Material
Functional Unit Testing
Build & Config & Unit Testing
Development
Oct
Nov
Dec
Jan
Project Start
Change Mgt.
TM1 (T8A), SRC2
Single Role Build
Job/Composite Role Design
Job/Comp. Role Build
SAP
Authorization
TM0, SRC1
BW Queries & S4 HANA Gap analysis & build
Local extractor analysis & build
Dashboard analysis & configure
SIT
Go Live
TM2
GL Sim
TM2, SRC1
GLS (T8A)
Productive P2A
Hypercare
Functional Data Val.
2 weeks
6 weeks
6 weeks
15 weeks
Hypercare
Go Live
Dual Maintenance
Prep
Train-the-Trainer
Related Projects
5 weeks
Project
Soft Freeze
DR
1 week
8 weeks
12 weeks
8 weeks (18.8. -10.10.)
5 weeks (3.3. – 04.04.)
14 weeks
Project Management (Financial, Gov)
Interface Planning
Add-Ons
6 weeks
Dev BW to GDR
Analysis
Kick Off
TM0
11 weeks (07.04. – 20.06.)
TM1
8 weeks (23.06. – 15.08.)
EU Training
Vacation period
Feb
March
April
Cut Over
6 weeks
6 weeks (13.10. – 21.11.)
2025
Single Role Design
2026
Testing
27 weeks
6 weeks
Change Freeze
TM0 Unit Test
Dress Reh
3 weeks (2. – 20.02.)
09.03.26
Cut Over Prep
UAT
Functional Data Validation
9 weeks (24.11. – 23.1.)
Single Role Test
Comp. Role Test
Mapping EU
EU Simulation

## Slide 10
10
Thank you